## Sheet1
User Stories | Description | Priority | Est | ETA | Assigned to | Item # | Status | Progress: | 100 | %
As a player I want to browse the menu to select an option | Design basic user interface menu | High | 25 |  | Loi | 1 | Done | 25
| Design detailed graphical user interface | Low | 10 |  | Loi | 2 | Done | 10
As a player I would like to select "Play Game" from the menu so I can access battle mode | Link battle mode to menu interface | High | 10 |  | Andee | 15 | Done | 10
| Design play mode option in menu | Med | 15 |  | Multiple |  | Done | 15
As a player I would like to be able to select "Load" or "Create" player in order to make my profile | Link create user profile in menu | High | 5 |  | Marc | 3 | Done | 5
| Link load user profile in menu | Med | 5 |  | Marc | 16 | Done | 5
| Create Player profiles | High | 15 |  | Marc | 17 | Done | 15
As a player I want to select "View Ranking" to see my statistics so I can compare it with others | Display user score data (Average and games played) | High | 10 |  | Marc | 4 | Done | 10
| Display user ranking | Med | 5 |  | Aiden | 5 | Done | 5
| Save profile to output file function | High | 25 |  | Aiden | 12 | Done | 25
| View other players scores | Med | 10 |  | Aiden | 6 | Done | 10
| Design view stats option | Med | 10 |  | Loi |  | Done | 10
As a player I want to be able to see my battle options in order to select a dice roll option | Provide method to simulate dice roll | High | 5 |  | Andee | 7 | Done | 5
| Display statistical options and points values | High | 20 |  | Andee | 8 | Done | 20
| Select attack and compare scores | High | 15 |  | Jessie | 9 | Done | 15
As a player I want to be able to attack a monster by rolling dice so I can defeat the monster | Create CPU player profiles | Med | 5 |  | Andee | 11 | Done | 5
| Update scores after rolls | High | 10 |  | Jessie | 10 | Done | 10
As a player I would like to be able to defeat monsters so that I can progress to the next level | Create win condition for defeating final boss | Med | 5 |  | TBA | 13 | Done | 5
| Update player global score | High | 10 |  | Marc | 14 | Done | 10
| SCRUM Master (Ninja) |  |  |  | Andee
Instructions: Objective of the game is to guess the number closest to the dealer's number. You begin by selecting what number you think will appear and depending on your choice you can earn more or less points based on the probability of that number landing. A CPU will also roll and compete with you, winning more points/rounds than the computer after 3 rounds will advance you to the next stage.