## Sheet1
User Stories | Description | Priority | Est | ETA | Assigned to | Item # | Status | Progress: | 41.6667 | %
As a player I want to browse the menu to select an option | Design basic commandline user interface menu | High | 15 |  | Loi | 1 | Done | 15
| Design graphical user interface | Low | 30 |  | Loi | 2 | In Progress
As a player I would like to select "Play Game" from the menu so I can access battle mode
| Design play mode option | Med | 20 |  | Float |  | In Progress
| Create user profile | High | 15 |  | Marc | 3 | Done | 15
As a player I want to select "View Ranking" to see my statistics so I can compare it with others | Display user score data (Average and games played) | High | 10 |  | Marc | 4 | Not started
| Display user ranking | Med | 10 |  | Aiden | 5 | Not started
| Save profile to output file | High | 20 |  | Aiden | 12 | Done | 20
| View other players scores | Med | 10 |  | Aiden | 6 | Not started
| Design view stats option | Med | 10 |  | Float |  | Not started
As a player I want to be able to see my battle options in order to select a dice roll option | Provide method to simulate dice roll | High | 10 |  | Andee | 7 | Done | 10
| Display statistical options and points values | High | 20 |  | Andee | 8 | Done | 20
| Select attack and compare scores | High | 20 |  | Jessie | 9 | Done | 20
| Link battle mode to menu interface | High | 10 |  | Andee | 15 | In Progress
As a player I want to be able to attack a monster by rolling dice so I can defeat the monster | Create CPU player profiles | Med | 10 |  | Andee | 11 | In Progress
| Update scores after rolls | High | 10 |  | Jessie | 10 | In Progress
As a player I would like to be able to defeat monsters so that I can progress to the next level | Create win condition for defeating final boss | Med | 10 |  | TBA | 13 | Not started
| Update player global score | High | 10 |  | Marc | 14 | In Progress
| SCRUM Master (Ninja) |  |  |  | Andee
Instructions: Objective of the game is to guess the number closest to the dealer's number. You begin by selecting what number you think will appear and depending on your choice you can earn more or less points based on the probability of that number landing. A CPU will also roll and compete with you, winning more points/rounds than the computer after 3 rounds will advance you to the next stage.